## Hybrid Project Plan
| PROJECT NAME | STUDENT/TEAM | START DATE | END DATE |  | OVERALL PROGRESS |  |  | PROJECT DELIVERABLE
|  |  | 2024-04-08 | 2023-06-17 |  | 0% |  |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | HOURS | STATUS | COMMENTS
| Project Plan | Research | Your name | 50% | 2024-04-08 | 2024-07-17 | 101 | 0 | Not Started
| Models/3rd Person Programming | Art | Jon | 0% |  |  |  |  | Not Started
| 3rd Person Programming | Programming | Jon | 0% |  |  |  |  | Not Started
| Enemy Programming/First Person Programming | Programming | Jon | 0% |  |  |  |  | Not Started
| Animation | Animation | Jon | 0% |  |  |  |  | Not Started
| Animation/Audio | Sound | Jon | 0% |  |  |  |  | Not Started
| Level Design | Configuration | Jon | 0% |  |  |  |  | Not Started
| Polish | Final | Jon | 50% |  |  |  |  | Not Started
| Sprint 1 : Models/3rd Person Programming | Milestone |  | 0% | 2024-04-22 | 2024-04-29 | 0 | 7.75 | Complete
| Slopes | Art | Jon |  |  |  |  | 0.25 | Complete | Added extra center vertices to be able to stretch the UV to fit with the Shader
| Hands | Art | Jon |  |  |  |  | 1 | Complete
| Interact Button | Art | Jon |  |  |  |  | 1 | Complete
| Key | Art | Jon |  |  |  |  | 1 | Complete
| Door | Art | Jon |  |  |  |  | 1 | Complete
| Move | Programming | Jon |  |  |  |  | 0.5 | Complete
| Jump | Programming | Jon |  |  |  |  | 1 | Complete
| Attack (Begin) | Programming | Jon |  |  |  |  | 2 | Complete
| Sprint 2: 3rd Person Programming | Milestone |  | 0% | 2024-04-29 | 2024-05-06 | 0 | 8 | Complete
| Attack (Finish) | Programming | Jon |  |  |  |  | 2 | Complete
| Enemy Detection | Programming | Jon |  |  |  |  | 0.5 | Complete
| Ranged Attack | Programming | Jon |  |  |  |  | 1.5 | Complete
| Pathfinding (Begin) | Programming | Jon |  |  |  |  | 4 | Complete
| Sprint 3: Enemy Programming/First Person Programming | Milestone |  | 0% | 2024-05-06 | 2024-05-13 | 0 | 17 | Complete
| Pathfinding (Finish) | Programming | Jon |  |  |  |  | 4 | Complete | Pathfinding took longer than expected. Nothing went wrong in particular, just underestimated time required
| Map Editor {{ADDED}} | Programming | Jon |  |  |  |  | 8 | Complete | Map Editor was easier to make AI Pathfinding easier.
| Move the Movables | Programming | Jon |  |  |  |  | 2 | Complete | Delayed due to Pathfinding
| Input Feedback | Programming | Jon |  |  |  |  | 1 | Complete
| Freeze/Stun Enemies | Programming | Jon |  |  |  |  | 2 | Complete
| Sprint 4: Animation | Milestone |  | 0% | 2024-05-13 | 2024-05-20 | 0 | 7.5 | Complete | Delayed due to Programming taking longer than exxpected
| Blender Animation Research | Research | Jon |  |  |  |  | 2 | Cancelled | No longer requires since scale of meshes is closer to normal
| Walk | Animation | Jon |  |  |  |  | 1 | Complete
| Idle | Animation | Jon |  |  |  |  | 0.5 | Complete | Must be redone
| Attack | Animation | Jon |  |  |  |  | 4 | Complete | Scope Changed, only one attack animation, bring back other two if time during polish
| Sprint 5: Animation/Audio | Milestone |  | 0% | 2024-05-20 | 2024-05-27 | 0 | 8.5 | Complete
| Jump | Animation | Jon |  |  |  |  | 1 | Complete
| Death | Animation | Jon |  |  |  |  | 1 | Complete
| Ranged Attack | Animation | Jon |  |  |  |  | 0.5 | Complete
| Hookup Animations | Animation | Jon |  |  |  |  | 2 | Complete
| Find Audio Samples | Sound | Jon |  |  |  |  | 2 | Complete
| Implement Audio | Sound | Jon |  |  |  |  | 2 | Complete
| Sprint 6: Level Design | Milestone |  | 0% | 2024-05-27 | 2024-06-03 | 0 | 8 | Complete
| Level Design (as many as possible) | Configuration | Jon |  |  |  |  | 8 | Complete
| Sprint 7: Polish | Milestone |  | 50% | 2024-06-03 | 2024-06-10 | 0 | 8 | Complete
| Main Menu | Configuration | Jon |  |  |  |  | 2 | Complete
| Pause Menu | Configuration | Jon |  |  |  |  | 2 | Complete
| Polish | Configuration | Jon |  |  |  |  | 4 | Complete
| Final Project | Polishing and Preparing Presentation |  | 25% | 2024-06-10 | 2024-06-17 |  |  | In Progress
| Final Delivery | Final |  | 25% | 2024-04-22 | 2024-06-17 |  |  | Not Started
Note on A5: Mark with X to Discuss about the risks

## Data
FEATURE TYPE
Art
Programming
Documentation
Research
Animation
Sound
Project Setup
Configuration
""
Final